## SQA Review Checklist
SQA Review Checklist v 1.1
Project Name: Red Turf | Project Manager: Nagoor Inaganti | Current Phase: | Phase II
SQA: |  | Date of Review: | 2019-05-05
Description | Artifact Required | Reviewed Yes/No | Remarks
Action points
Whether previous week action points are closed.(From MOMS, WSM, etc) | MOM | Yes
Whether SQA observations are closed. | Review Observations | Yes
Customer issues, If any, are tracked till closure.
Project Initiation & Project Planning
PIN available for the project | KOM Check list | Yes
Project Goals are appropriately defined |  | Yes
Whether Kick-off Meeting conducted as per checklist? | KOM Check list | Yes
Kick-off Meeting MOM available and all the action items identified are tracked to closure | MOM | Yes
PMP prepared, Reviewed and approved? | PMP | Yes
PMP revisited periodically |  | Yes
QMP prepared, Reviewed and approved | QMP | Yes
Are the Assumptions documented in PMP? | Assumptions | Yes
Project Planning Documented in PMP | Project management plan | Yes
Quality management plan prepared? | Quality management plan | Yes
Risk Tracker prepared and approved | Risk Tracker | Yes
PMC - Project Monitoring and Control
Are the weekly Status reports available? | Status Reports | Yes
Status of project training activities. | Training plan | Yes
Are the Steering Committee meeting records available? | MOM, Any other records | Yes
Is the effort logged by each individual? | Timesheet | Yes
Are the Timesheets approved for all team members | Timesheet approved | Yes
Meetings (Team, Offshore-Onsite, Customer) are happening regularly as defined in PMP | MOM | Yes
MOMs available for the meetings? |  | Yes
Weekly status report (WSR) sent to onsite/ Customer regularly | WSR/ Check in server | Yes
Customer feedback captured and recorded in the Customer Feedback Log | Customer Feedback Form | Yes
Customer satisfaction Survey conducted as defined | Customer Satisfaction Survey Report | Yes
Risk tracker updation based on Status | Risk tracker | Yes
The tools being used are tested and records maintained? |  | Yes
The status of Data Management activities discussed ? |  | Yes
Metrics collected and Analyzed | Matrics Analysis Reports | Yes
CAR conducted as defined in QMP | CAR Report | Yes
RM - Requirements Management
Is there a clear understanding of the work(Requirements) (Check for Requirements document, - mail or hard copy signoff) | Requirement Doc | Yes
Requirements sign off by the customers |  | Yes
Requirements matrix | Requirements Traceability Matrix | Yes
Have the changes to requirements managed by a process (CR Process) |  | Yes
CRF present? |  | Yes
Check for the change history for a artifact which has undergone changes | Change request form | Yes
Are Requirements traceable through different phases; Is traceability maintained between the requirements? (Check for Bi-directional Traceability) | Requirements Traceability Matrix | Yes
Configuration management
CMP available for the project | Configuration Management Plan | Yes
Is CMP reviewed and approved | Review Record | Yes
The customer supplied products are verified periodically? |  | Yes
Whether coding standards are checked in configuration tool. |  | Yes
Tailoring document is checked in configuration tool |  | Yes
Latest versions of all documents,source code,reports,MOM's are checked in configuration tool. |  | Yes
Is Configuration Status accounting is done | Configuration Status Accounting Report | Yes
Configuration audits conducted as defined in the CMP | Functional Configuration Audit Report & Physical Configuration Audit Report | Yes
General
If any previous documents, source code has been used in the project so far, whether this information is entered into the process data base (PDB) ? |  | Yes
Status of Defect prevention activities. | CAR Report | Yes
Whether lessons learnt are prepared and maintained in PPD(Project and product database) |  | Yes
Coding stage
Coding guidelines/ standards available |  | Yes
All the Code Components are reviewed | Code Review Report | Yes
Header and Revision History is maintained for the code components |  | Yes
Code Review comments incorporated |  | Yes
Code components baselined |  | Yes
Whether the RTM record updated with the reference to code components. |  | Yes
Unit Test Plan available | Unit Test Plan | Yes
Unit Test cases reviewed and baselined | UT Test case Review Report | Yes
Unit Testing caried out | Test Report | Yes
Unit Test defects/ feedback recorded and defects are tracked to closure |  | Yes
Testing stage
Is the Test Plan prepared | Test Plan | Yes
Test Plan reviewed and approved | Review Report/ Approval record | Yes
Test Plan baselined |  | Yes
Test Cases Prepared, Reviewed and approved | Test Case Document | Yes
Test Cases baselined | Test Case Document | Yes
Status of Unit/Integration/System /Alpha/Beta Testing. |  | Yes
Whether the RTM record updated with the status. | RTM | Yes
Release stage
Is the Build Plan available? | Build Plan | Yes
Release Note prepared | Release Note | Yes
Build prepared as per the Build Plan |  | Yes
Build readiness review conducted | Release Readiness Review Checklist | Yes
All the review issues addressed |  | Yes
Post release stage
Status of post release bugs if any? |  | Yes
Status of change requests if any? |  | Yes
Are the Defcts analyzed? |  | Yes
Impact analysis reports available for the defects |  | Yes
Defect status updated in the defect tacking tool |  | Yes
| Reviewed | 2019-05-05